## Team
Initials | First | Last | Email | GitHub Username
ik | Ian | Klien
tk | Tejas | Karelia | tkarelia@stevens.edu | tejaskarelia17
GitHub Repository:

## Backlog
Sprint | Story ID | Story Name | Owner | Status
No Backlogs

## Burndown
Date | Remaining Stories | Story Velocity | LOC. | Min. | Code Velocity
2016-10-06 | 10 | N. A. | 0 | N. A. | N. A.
2016-10-12 | 6 | 4 | 250 | 120 | 125

## Sprint1
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
JC01 | Display Screen | ik | Done | 150 | 60 | 120 | 90 | 2016-10-07
T01.01 | Develop a screen | ik
T01.02 | Screen able to display input number | ik
T01.03 | Screen able to display operation | ik
T01.04 | Screen able to display output number
JC02 | Display Numbers 0 -9 | ik | Done | 150 | 60 | 120 | 90 | 2016-10-10
T02.01 | Develop buttons that indicate numbers from 0 - 9 | ik
T02.02 | Store input1 value | ik
T02.03 | Display input1 on screen | ik
JC03 | Display Addition Operation | ik | Done | 150 | 60 | 120 | 90 | 2016-10-10
T03.01 | Develop a button '+' | ik
T03.02 | Store add operation in memory | ik
T03.03 | Clear screen for input2 | ik
JC04 | Display Addition Operation | ik | Done | 150 | 60 | 120 | 90 | 2016-10-12
T04.01 | Develop a button '=' | ik
T04.02 | Compute addition of input1 and input2 | ik
T04.03 | Display output | ik
Review Results
Keep doing:
Avoid:

## Sprint2
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
Review Results
Keep doing:
Avoid:

## Sprint3
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
Review Results
Keep doing:
Avoid:

## Sprint4
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
Review Results
Keep doing:
Avoid:

## Stories
Story ID | Story Name | Story Description
JC01 | Dislpay Screen | Develop a Screen where the input numbers, operations and output result will be displayed.
JC02 | Display Numbers 0 - 9 | Develop buttons on the calculator to represent numbers from 0 to 9.
JC03 | Display Addition Operation | Develop 'Add' button that performs addition operation.
JC04 | Display Compute Operation | Develop '=' button that computes the calculation.
JC05 | Display Substraction Operation | Develop 'substraction' button that performs substraction operation on the input.
JC06 | Display Clear Operation | Develop '<-' button that clears the input.
JC07 | Display Multiplication Operation | Develop 'multiplication' button that performs substraction operation on the input.
JC08 | Display Reset Operation | Develop 'Reset' button that resets the entire calculator.
JC09 | Display Division Operation | Develop 'division(/)' button that performs substraction operation on the input.
JC10 | Display Alert Box | Catch error if a number is divided by zero and display alert box saying "Division by ZERO not possible!"