## Team
Initials | First | Last | Email | GitHub Username
ik | Ian | Klien | iklein@stevens.edu | Maestrodobis
tk | Tejas | Karelia | tkarelia@stevens.edu | tejaskarelia17
GitHub Repository: |  |  | https://github.com/Maestrodobis/Calculator_546

## Backlog
Sprint | Story ID | Story Name | Owner | Status
2 | JC04 | Develop Screen | ik | NC
2 | JC05 | Display Numbers 0-9 | tk | NC
No Backlogs

## Burndown
Date | Remaining Stories | Story Velocity | LOC. | Min. | Code Velocity
2016-10-06 | 11 | N. A. | 0 | N. A. | N. A.
2016-10-12 | 8 | 3 | 111 | 120 | 55.5

## Sprint1
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
JC01 | Input Command for Number 1 | ik | Done | 20 | 10 | 120 | 20 | 2016-10-07
T01.01 | Ask the user for input1 | ik
T01.02 | Store input1 | ik
T01.03 | Display input1 | ik
JC02 | Input Command for Number 2 | ik | Done | 20 | 10 | 120 | 20 | 2016-10-10
T02.01 | Ask the user for input2 | ik
T02.02 | Store input2 | ik
T02.03 | Display input2 | ik
JC03 | Add, Substract, Multiply and Divide | ik | Done | 20 | 20 | 19 | 20 | 2016-10-12
T03.01 | Compute input1 + input2 | ik
T03.02 | Compute input1 - input2 | ik
T03.03 | Compute input1 * input2 | ik
T03.04 | Compute input1 / input2 | ik
T03.05 | Display all the outputs | ik
Review Results
Keep doing:
what we are doing. Pretty consitent
Avoid:
Making dumb mistakes. Always error check when you go and there will be less bugs.

## Sprint2
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
Review Results
Keep doing:
Avoid:

## Sprint3
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
Review Results
Keep doing:
Avoid:

## Sprint4
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
Review Results
Keep doing:
Avoid:

## Stories
Story ID | Story Name | Story Description
JC01 | Input Command for Number 1 | Ask the user to input1 a number in commandline
JC02 | Input Command for Number 2 | Ask the user to input2 a number in commandline
JC03 | Add, Substract, Multiply and Divide | Should display the Added, Substracted, Multiplied and Divided output of the entered inputs.
JC04 | Develop Screen | Develop a Screen where the input numbers, operations and output result will be displayed.
JC05 | Display Numbers 0 -9 | Develop buttons on the calculator to represent numbers from 0 to 9.
JC06 | Display Addition Operation | Develop '+' button that clears the input.
JC07 | Display Subtraction Operation | Develop '-' button that clears the input.
JC08 | Display Multiplication Operation | Develop 'multiplication' button that performs substraction operation on the input.
JC09 | Display Reset Operation | Develop 'Reset' button that resets the entire calculator.
JC10 | Display Division Operation | Develop 'division(/)' button that performs substraction operation on the input.
JC11 | Display Alert Box | Catch error if a number is divided by zero and display alert box saying "Division by ZERO not possible!"