## Team
Initials | First | Last | Email | GitHub Username
ik | Ian | Klien | iklein@stevens.edu | Maestrodobis
tk | Tejas | Karelia | tkarelia@stevens.edu | tejaskarelia17
GitHub Repository: |  |  | https://github.com/Maestrodobis/Calculator_546

## Backlog
Sprint | Story ID | Story Name | Owner | Status
2 | JC04 | Develop Screen | ik | Completed
2 | JC05 | Display Numbers 0-9 | tk | Completed
No Backlogs

## Burndown
Date | Remaining Stories | Story Velocity | LOC. | Min. | Code Velocity
2016-10-06 | 13 | N. A. | 0 | N. A. | N. A.
2016-10-12 | 10 | 3 | 111 | 120 | 55.5
2016-10-19 | 7 | 3 | 181 | 140 | 30
2016-11-09 | 5 | 2 | 290 | 160 | 40.875
2016-11-30 | 0 | 5 | 323 | 60 | 33

## Sprint1
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
JC01 | Input Command for Number 1 | ik | Done | 20 | 10 | 120 | 20 | 2016-10-07
T01.01 | Ask the user for input1 | ik
T01.02 | Store input1 | ik
T01.03 | Display input1 | ik
JC02 | Input Command for Number 2 | ik | Done | 20 | 10 | 120 | 20 | 2016-10-10
T02.01 | Ask the user for input2 | ik
T02.02 | Store input2 | ik
T02.03 | Display input2 | ik
JC03 | Add, Substract, Multiply and Divide | ik | Done | 20 | 20 | 19 | 20 | 2016-10-12
T03.01 | Compute input1 + input2 | ik
T03.02 | Compute input1 - input2 | ik
T03.03 | Compute input1 * input2 | ik
T03.04 | Compute input1 / input2 | ik
T03.05 | Display all the outputs | ik
Review Results
Keep doing:
what we are doing. Pretty consitent
Avoid:
Making dumb mistakes. Always error check when you go and there will be less bugs.

## Sprint2
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
JC04 | Develop Screen | tk | Done | 50 | 30 | 46 | 35 | 2016-10-14
T04.01 | Set height and width for the screen | tk
T04.02 | Allow only 10 digits on the screen | tk
T04.03 | Display Screen | tk
JC05 | Display Numbers 0 -9 | ik | Done | 45 | 30 | 52 | 25 | 2016-10-17
T05.01 | Set dimensions for number buttons | ik
T05.02 | Position all buttons appropriately | ik
T05.03 | Display all buttons | ik
JC06 | Display Operations | ik | Done | 70 | 60 | 64 | 55 | 2016-10-19
T06.01 | Develop '+' button with same dimensions | ik
T06.02 | Develop '-' button with same dimensions | tk
T06.03 | Develop '*' button with same dimensions | tk
T06.04 | Develop '/' button with same dimensions | ik
T06.05 | Display all buttons | ik
Review Results
Keep doing:
Continuously checking the code and commenting the code for portability.
Avoid:
Wasting time on features not present in the user story.

## Sprint3
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
JC07 | Display numbers on screen | ik | Done | 30 | 25 | 35 | 25 | 2016-10-29
T07.01 | Set font of the printed numbers | ik
T07.02 | Set the alignment of the numbers printed | ik
T07.03 | Display numbers on the screen | ik
JC08 | Reset Operation | ik | Done | 50 | 30 | 46 | 35 | 2016-11-04
T08.01 | Set dimensions for reset button | ik
T08.02 | Position the button appropriately | ik
T08.03 | Reset and Clear the screen on-click | ik
Review Results
Keep doing:
Finish before deadline.
Avoid:
Keep the code structure clean and maintain indentation.

## Sprint4
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
JC09 | Addition Operation | ik | Done | 10 | 15 | 12 | 11 | 2016-11-08
T09.01 | Accept input numbers | ik
T09.02 | Perform addition | ik
T09.03 | Display result on the screen | ik
JC10 | Substraction Operation | ik | Done | 10 | 15 | 12 | 12 | 2016-11-16
T10.01 | Accept input numbers | ik
T10.02 | Perform substraction | ik
T10.03 | Display result on the screen | ik
JC11 | Multiplication Operation | ik | Done | 10 | 15 | 12 | 13 | 2016-11-24
T11.01 | Accept input numbers | ik
T11.02 | Perform multiplication | ik
T11.03 | Display result on the screen | ik
JC12 | Division Operation | ik | Done | 10 | 15 | 12 | 13 | 2016-11-27
T12.01 | Accept input numbers | ik
T12.02 | Perform division | ik
T12.03 | Display result on the screen | ik
JC13 | Display Infinity | ik | Done | 13 | 15 | 10 | 11 | 2016-11-30
T13.01 | Accept input numbers | ik
T13.02 | Check if 1st input is divided by zero | ik
T13.03 | Display "Infinity" | ik
Review Results
Keep doing:
Refactoring the code.
Avoid:
Missing scrum meetings.

## Stories
Story ID | Story Name | Story Description
JC01 | Input Command for Number 1 | Ask the user to input1 a number in commandline
JC02 | Input Command for Number 2 | Ask the user to input2 a number in commandline
JC03 | Add, Substract, Multiply and Divide | Should display the Added, Substracted, Multiplied and Divided output of the entered inputs.
JC04 | Develop Screen | Develop a Screen where the input numbers, operations and output result will be displayed.
JC05 | Display Numbers 0 -9 | Develop buttons on the calculator to represent numbers from 0 to 9.
JC06 | Display Operations | Develop buttons that represent 'Addition', 'Substraction, 'Multiplication', 'Division', 'Reset' and 'AC'
JC07 | Display Numbers on Screen | Develop a logic that displays the types numbers.
JC08 | Reset Operation | Develop 'Reset' button that resets the entire calculator.
JC09 | Addition Operation | Develop '+' button that performs multiplication operation on the input.
JC10 | Substraction Operation | Develop '-' button that performs multiplication operation on the input.
JC11 | Multiplication Operation | Develop '*' button that performs multiplication operation on the input.
JC12 | Division Operation | Develop 'division(/)' button that performs substraction operation on the input.
JC13 | Display Infinity | Catch error if a number is divided by zero and display alert box saying "Infinity"